Free Cataract Surgery Camp

28th October to 30th October,2025 (11th Kartik to 14th Kartik 2082) Key Points

| Main Organizer | : Rotary Club of Kawasoti in Collaboration with Tilganga Institute of Ophthalmology (TIO), Kathmandu |
| --- | --- |
| Local Host | : |
| Main Sponsors | : |
| Partners in Action | : 1. Rotaract Club of Kawasoti 2.Rotary Club of Chitawan |
|  | 3. Rotary Club of Pokhara Annapurna |
|  | 4. Rotary Club of Kathmandu Bagmati |
|  | 5. Rotary Club of Patan |
| Supported By | : 1. Anvi Memorial Trust |
|  | 2. Madhyabindu Multiple Campus |
|  | 3. PABSON Nawalpur |

Nos of Screening Camps: 	10

Nos of Visitors in Screening 	2500+ Nos of New visitors at Camp 1000+

Total Screening 	 	 	3500+

Cataract Finding  	 	 	500+     All cataracts are not eligible for surgery due

Eligible Cataract for Surgery 	400+ 	due to their Health Status (Blood Sugar, Blood Pressure,

other blood related causes and infections)

| Cost Plan: |  |  |
| --- | --- | --- |
| Screening Camp Cost: 33500 X 10 |  | =3,35,000 |
| Hospitality and Logistic for Surgical Team |  | 2,08,500 |
| Cereology Test of 500 cases (750 X500) |  | 3,75,000 |
| Other Logistics during surgical camp |  | 2,83,000 |
| Total Cost of Project Details of Costing: 1.Screening Camp Cost: Promotion and publicity 5,000 Optometric 1 2,500 Assistant 1 1,000 Medicine for 250 Visitors (LS) 15,000 Vehicle 5,000 |  | 12,01,500 |
| Lunch, Snacks & Others 5,000 | 33,500 |  |

2. Hospitality and Logistic for Surgical Team  	 	 	 	2,08,500

Nos of member in Surgical Team  	 	+/- 15

Stay  cost (4 Days)  	 	          1,14,000

Break Fast (4 Days)   (15 X4 X300)  	18,000  	Snacks       (4 Days)   (15 X4 X150)  	  9,000

Lunch         (5 Days)   (15 X5 X500)  	37,500

Dinner       (4 Days)    (15 X4 X500)               30,000

Room 	Surgeon 3  (Single Room)    3X3500X4 	42,000

Others   12 (Double Room)  6X3000X4 	72,000

4. Other Logistics 	 	 	 	 	 	 	 	2,83,000

Food for Volunteers(Lunch/Snacks)  25000 X3 	 	75,000

Vehicle & Conveyances for Volunteers (3 days) 	 	18,000  	Opening & Closing Ceremony Cost (LS) 	 	 	30,000

Bus (Patients Pickup/ Drop Off from Screening Venue) 	75,000

Food/ Tea/Snacks for patients     60,000  Media & Promotion Cost     25,000

Note:  All surgical cost including clinic Setup, surgical medicine, Surgeon and post op medicine including travel cost of surgical team is born by Tilganga Institute Ophthalmology. So this is not included in budgetary system.

We do cereology test for all cataract identified people before starting the surgery process.  After the test few are rejected for surgery. We do check Blood Sugar, Blood Pressure, HIV, HbsAG & HCV for every cataract identified people.